## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | M.R.Tejeshwar Reddy | 2025-11-06 | AI model incorrectly classified genuine Aadhaar as fake. | Sprint 1 | M.R.Tejeshwar Reddy | Functional | Improved dataset and retrained model | 2025-11-10 | Closed | Accuracy improved by 45%
2 | M.R.Tejeshwar Reddy | 2025-11-15 | Dashboard UI not displaying verification results | Sprint 2 | M.R.Tejeshwar Reddy | UI/UX | Fixed Frontend | 2025-11-20 | Closed | Verified in testing
3 | M.R.Tejeshwar Reddy | 2025-11-21 | Unable to decode the aadhaar qr code. | Sprint 3 | M.R.Tejeshwar Reddy | Functional | Implemented developed modules | 2025-11-25 | Closed | Not authorised to decode qr code

## Sheet2
Logical
User Interface
Maintainability
Standards
Others